## UAT Point
No | Module | Task Description | Issues Remarks | Internal Requirement Gathering Date | Delivery Date | Status | Devevloper Testing Status | Functional Testing Remarks | Testing By Functional Date | Developer Status Remarks after testing / API End point | Assign To
1 | Sales Quote | After Saving, In Justification box of Sales Quote Approval, Target Date should be after Negative Credit Limit. |  |  |  | Complete by CRM Side | Done |  | 2026-03-01
|  | In Sales Quote Approval process, if the case is of only Negative Margin then in justification, only Negative Margin should appear and same in the message. In case of only Negative Credit Limit, in justification, Negative CreditLimit and Target Date should appear and message should only mention Negative Credit Limit. |  |  |  | Complete by CRM Side | Done |  | 2026-03-01
|  | Sales Quote page in Finance login for Approval - took too much time to load, didn't load the Quote Details section - Location and Customer details, the data in the fields of Total Expo, Overdue, Avg. Delay Days didn't appear, in Customer Outstanding Overdue report section, need a new field of Margin - Costsheet margin value of Invoice to be shown. Total Days = Current Date - Bill Date; Overdue Days = Current Date - Due Date. In Last 10 Sales Quote data, more than 10 data were appearing and some of them were repeating. |  |  |  | Complete by CRM Side | Done | Margin field not there. Logic of Total Days is remaining to check.
|  | In Negative Margin Approval mail to HOD, need to keep MSNAV ID in CC - but not in Negative Credit Limit (Finance) approval mail. In Approved/Rejected mail of the Quote, in both, include MSNAV Email ID in CC. |  |  |  | Complete by CRM Side | Done | Need to plan this with Rikesh sir | 2026-03-09
|  | Quote Date should be non-editable. |  |  |  | Complete by CRM Side | Done |  | 2026-03-01 | Not issue
|  | When Sales Quote craeted from Inquiry, all the details should be visible in the Sales quote - auto trigger when sales quote is generated. | Rework |  | 2026-03-09 | Complete by CRM Side |  | Contact details are only appearing when clicked on the contact name. | 2026-03-01 | We have fixed the issue based on the description. Now we need to confirm what needs to be done next
|  | When payment terms, Inco terms, transport method and Delivery date - will be updated in 1st product line details. When doing 2nd product line details update, the same fields should be non-editable (should be locked in 1st product line update itself. |  |  |  | Complete by CRM Side | Done | When sales quote created from Inquiry, the fields of Inco terms and Transport payment method - remains non-editable from the beginning itself. | 2026-03-01 | Done
|  | Approval mail format changes - as provided by PCAPL team. Also, add Justification in inverted commas beside header in mail. |  |  |  | Complete by CRM Side | Done | Couldn't show Justification message in inverted commas due to developer limitation. Hence showed as - Justification: <Justification message> | 2026-03-09
2 | Daily Visit | In Daily Visit list page, there should be an "EDIT" action for changing the details in the Daily Visit card. | Rework |  | 2026-03-09 | Complete by CRM Side |  | When clicked on "Edit" and changed some details in exisiting daily visit entry card and saved, the details were not updated. It remained the same as before. | 2026-03-01 | Done
3 | Contact | Provide action of - Create Inquiry on Contact card page just like Create Sales Quote. |  |  |  | Complete by CRM Side | Done |  | 2026-03-05
4 | Customer List | Remove SP Code from Customer list |  |  |  | Complete by CRM Side | Done |  | 2026-03-05
5 | Inquiry | Inquire Date - Editable = False |  |  |  | Complete by CRM Side | Done |  | 2026-03-03
|  | Email field should not be text field |  |  |  | Complete by CRM Side | Done |  | 2026-03-05
|  | Provide validations - in creating contact person from Inquiry. |  |  |  | Complete by CRM Side | Done |  | 2026-03-05
|  | Delivery Date should not be mandatory in Inquiry card. |  |  |  | Complete by CRM Side | Done |  | 2026-03-05
|  | Provide "Save & Sales Quote" action in Inquiry card. On click, the Inquiry to be saved and sales quote card page with inquiry details to open. |  |  |  | Complete by CRM Side | Done |  | 2026-03-05
|  | When creating Contact from the Inquiry, when clicked on "Back", the user should be redirected back to Inquiry. |  |  |  | Complete by CRM Side | Done | On saving, it was redirected to the Inquiry page, but in Inquiry, the contact name didn't appear automatically. Had to select the contact manually. - Is it possible? | 2026-03-06 | Done
6 | Password Reset Issue | The Admin user is not able to change and reset the other user's passwords. |  |  |  | Complete by CRM Side | Done |  | 2026-03-06
7 | Dashboard | A raw data report to be created - for customers against whom Business Plan or Invoice is done, any of the two. As per this report, filtered data to be shown in the various sections in Dashboard. The excel file will be provided by Pcapl. | Report is required to be prepared as per the report of old Format. When clicked on the sales person an option require to view the grouping as per customer or as per product. When further drilled down from item require customer wise detail for that item, when drilled down from Customer require item wise detail. | 2026-02-23 | 2026-02-26 | Complete by CRM Side | Done | Data Mismatch. | 2026-03-09
|  | Top 10 Customers to be shown like Top 10 products. | Rework |  | 2026-03-09 | Complete by CRM Side |  | Currently, it shows Top 10 Customers in Top 10 Products section. Rather they require both separately. | 2026-03-05 | Done
|  | In every section, provide Date filter. By default, today's date filter. | Rework |  | 2026-03-09 | Complete by CRM Side |  | Date filter is provided but not working | 2026-03-13 | Done
|  | Remove Daily Visit section from Dashboard | please confirm on which user’s dashboard this should appear. Earlier, we updated a similar point and it was changed later, so please let me know whether to keep it or remove it completely | 12-02-2026-pending |  | Complete by CRM Side | Done |  | 2026-03-09
|  | Provide "New" action for creating Daily Visit in Today's Task section - on click, redirect it to Daily Visit card. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-05
|  | Provide "Company Name" filter option as default in Contact list. |  |  | 2026-02-12 | Complete by CRM Side | Done | Dropdown - Not possible | 2026-03-05
|  | Dashboard of Salesperson with actual statistics shows - "Mayur" as static value even when the login is of another salesperson. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-05
8 | Daily Visit | In Daily Visit list page, they require product details with competitor on the front page itself. Currently, it is available on clicking eye action. They require Product filter on the Daily Visit list page for that need product details upfront. | Add the field to this API for the Product Name and Competitor | I have added the api and Filed but can't be correct the api value | 2026-03-06 | Complete by CRM Side |  | Not Done. | 2026-03-09 |  | Praduman
|  | They require Daily Visit, Business Plan and Sales Quote details on list page - by clicking their respective actions from the contact list page itself. Also, on clicking that action, first the filter should open - Contact Name default, Product Name and Date filter. An option is to redirect directly to their respective pages by clicking the actions. |  |  | 2026-02-27 | Complete by CRM Side | Done | Date Filter not working in Daily Visit action. No action to go to their respective card pages. When opened Sales Quotes, without any Date filter, the Schedule Order field does not show any status and the "eye" icon which should have been in Products section - is visible in the Schedule Order part. Also, when Date filter applied in the Sales Quotes, the value of the filter does not remain and automatically shows all data after a few seconds. | 2026-03-09 | Not Issue | Praduman
9 | Contact | In contact card, requirement to provide lookup of All customers in contact name field. They want to know if similar name contact exists. Also, they require salesperson, PAN No. and GST No. to show along with the names. They require this for view purpose (informative) only. For that, if a similar contact exists, then they will click on that contact, and only General Fast tab and Contact Person details showing only Primary Contact detail should appear. Also, in existing contact detail - Save action to be disabled. | Pending Estimation from Pradyuman and aditya |  |  | Estimation Done
10 | Inquiry | In inquiry card, while creating new Delivery-To and Bill-To Addresses, Code field is mandatory which is manual. They require to auto-flow value in that field or which No. series setup to be created for both address fields. They require this everywhere where Bill-To and Delivery-To addresses can be created. | No. Series to be created in sales & receivable setup page for Ship-To Address and Job-To Address. When created new address and added, in BC the code should be created based on no. series. In CRM, no need of Code field in new addressess. | Pending BC Side I have Remove the code filed on CRM Side on - 05-03-2026 | 09-03-2026- Completed from BC side | Complete by CRM Side | Done CRM Side |  |  | InquiryDotNetAPI | Aditya
|  | Payment Terms to be shown at header level only. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-05
|  | Some fields are not required to be visible in list and card page. Sheet will be provided by pcapl team. | Pending from Prakash. Send Email as reminder | 12-02-2026-pending |  | Pending by BC Requirement |  |  |  |  | Diya
|  | In Inquiry Notification mail sent from list page, the requirement is to add a redirect link of BC. On clicking the link, the record of that inquiry should open in BC. - NEED to CONFIRM that this will be for users having access for BC only. What about the CRM users? | Aditya will provide link which will then be available in the mail. |  | 09-03-2026- Completed from BC side | Pending by API |  |  |  |  | Aditya
|  | In Inquiry list page, in Inquiry Product details, need to provide UOM code and not description in that field. Also, It should be beside Qty. field. |  | Aditya needs to update it. The UOM value must be changed by the BC team. | 09-03-2026- Completed from BC side | Pending by CRM |  |  |  | I have not received the field from the BC data flow | Aditya
11 | Sales Quote | Payment Terms to be shown at header level only. And, once the 1st product line inserted and saved, the fields of - Payment Terms, Inco Terms, and Transport Method should be locked [Editable = False]. | Rework |  | 2026-03-09 | Complete by CRM Side |  | Even in 1st line, the Inco Terms are locked when quote created from inquiry. | 2026-03-03 | Done
|  | In Transport Method field, in eye icon, the Transport rate card details did not appear even when created new record in the rate card. | Need to check on Confugration by Testing Team |  |  | Needs to check testing team
|  | Item availability details on product details did not appear. | Need to check on Confugration by Testing Team |  |  | Needs to check testing team
|  | Last three Transactions of customer - Requires Credit Days field - Logic = Payment Date - Invoice Date, if payment not yet done or partial payment done [open entry on CLE], then consider Today's Date instead of Payment Date. In case of closed CLE due to multiple payment entries, take last Payment entry Date in Payment Date. | Need to check on Confugration by Testing Team |  |  | Needs to check testing team
12 |  | In the Ordered Qty Details, the Remarks updated in the line level in Schedule order window does not appear. | Need to check on Confugration by Testing Team |  |  | Needs to check testing team |  | Not Done | 2026-03-09 | Done
|  | In Sales quote list page, provide an additional filter in Schedule order - Pending¦Partial. Both pending and partial status schedule orders will be visible. | Praduman sir will discuss further and update. |  | 2026-03-06 | Complete by CRM Side |  | Should appear as default. | 2026-03-09 |  | Praduman
|  | Assign To in Schedule order window - The logic is to send notification to the documents team (selected user) providing information about the order scheduled which needs invoicing now. In default, a particular user should appear. It would be upto the salesperson to manually change the user in case the default user not available. | 1. A boolean field of Documents team to be created in Employee master. 2. In Location card - New field - Documents User (show only document team = TRUE employees in the drop down. The user selected here will appear by default in Assign To field in schedule order window. |  | 09-03-2026- Completed from BC side | Complete by CRM Side |  |  |  | SalesQuoteDotNetAPI - OlDAPI. CodeunitEventMngt_MakeOrder - code unit salesquotes - new api | Aditya
|  | External Document No. should remain the same in the Partial case when doing scheduling 2nd time in the same quote. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-09
|  | They require attachment functionality on the Schedule order window for attaching External purchase order document. | At the moment alternate option is attaching the document on Sales order in BC |  |  | Complete by CRM Side | Done |  | 2026-03-09
|  | They require Purchase Order Date (Document Date) on the Schedule Order window beside External Document No. field |  |  | 2026-02-13 | Complete by CRM Side | Done | Need to know what date fields are used behind Document Date and Schedule Date as system only accepts both fields - equal values. | 2026-03-05 | Not issue
|  | Remarks and Assign To did not appear in ordered qty. details after inputing and selecting the same in Schedule Order window. |  |  |  | Complete by CRM Side | Done | Remarks did not appear. | 2026-03-06 | Done
|  | External Document No. and Document Date - show in Ordered Qty. Details and In Process Qty. Details. | Aditya will provide field in API and further will be done by Praduman sir |  |  | Complete by CRM Side | Done |  | 2026-03-06 |  | Aditya
|  | Provide Product details in Order Qty. Details, In Process Qty. Details and in Invoiced Qty. details - Product Name, Qty., Packing Style Code | Aditya will provide field in API and further will be done by Praduman sir |  | 09-03-2026- Completed from BC side | Pending by API |  |  |  | Done | Aditya
13 | Warehouse | Sorting does not work in Ongoing and Closed Task List page |  |  |  | Complete by CRM Side | Done |  | 2026-03-06
|  | In Ongoing/ Closed Task list page, To Location field - the value of the Ship-To location should appear. | Need to check Testing Team | Pending testing for testing Team |  | Complete by CRM Side | Done | Not Done. Check case SO No,: SDOM01198 | 2026-03-06 | If Vendor is set to ‘Yes’, the To Location field should display records based on the Vendor Location
|  | Transporter No. field caption change to - Transporter |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-06
|  | Contact No. do not show in Transporter rate card in BC | Hide the field. | contact no. value not showing the page on the BC side | 09-03-2026- Completed from BC side | Complete |  |  |  |  | Aditya
|  | Location card - Loading and unloading charges logic should work for CRM - system should fetch the Loading and Unloading charges per unit as per the Location card and auto calculate the value in the Loading/Unloading charges field irrespective of the Loading/Unloading Vendor selected. | New fields to be created - Loading charges per unit and Unloading charges per unit on Sales header. On creation of Sales order, values in these fields will be fetched from respective fields on location card selected on sales header. Then, in CRM, the charges will be auto-calculated [Loading Charges per unit * Transport Qty.] | Populate the loading vendor and unloading vendor with charges value for BC side | 09-03-2026- Completed from BC side | Pending by API |  |  |  |  | Aditya
|  | Driver Mobile No. field value - validation of 10 characters required. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-06
|  | Vehicle No. field value - space and special characters should not be allowed and the field value should only be upto 10 digits |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-06
|  | Asterisk mark required in Transporter No. and Vehicle No. field. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-06
|  | Require Partial Shipment functionality in Warehouse | In Warehouse Ongoing Task list page, for Document Type = "Sales Order", the Transport Qty on Product details will be editable. Also, provide Item Tracking "eye" icon line wise where the Item Tracking details will appear already filled by Salesperson at the time of scheduling the order. "Save" action to be provided line-wise. New fields of Line No. and Qty. Shipped to be provided in product details. | Pending from Diya - Scope to be prepared - 23-02-2026 Discussion | 09-03-2026- Completed from BC side | Complete by CRM Side |  |  |  | Warehouse_Sales_Details
|  | Require Wrap Text in Remarks field. |  |  | 2026-02-12 | Complete by CRM Side | Done |  | 2026-03-06
Need to show data - Branch-wise to warehousing users
|  | Cosmetic changes - spelling issues, LR/RR No., space between characters issue, etc. |  |  | 2026-04-22 | Complete by CRM Side | Done | Cosmetic changes pending - spelling, spacing issues, etc. | 2026-03-09
|  | Driver details does not appear when selected Transporter. Also, new driver no. added manually but did not appear in the list of drivers when filling details in another records selecting same Transporter | "+" action beside Driver Name field just like in Inquiry. User will update information of Driver Name, Mobile No. and Registration No. (License) and on Save, contact person of the Transporter will be created. | No need for change in 1st point. Working as expected. For 2nd point, Need to design a solution for this - Diya | 09-03-2026- Completed from BC side | Complete by CRM Side |  |  |  | Warehouse_Sales_Details
|  | In Ongoing Task List, the data should appear - Ascending of Order No. field and in Closed Task list, the data should appear - Descending of Order No. field by default. |  |  | 2026-02-23 | Complete by CRM Side | Done |  | 2026-03-09
|  | Caption change in Qty. field in Invoiced Qty. window - Qty. in MTS and remove UOM field |  |  | 2026-02-13 | Complete by CRM Side | Done | Caption not changed. | 2026-03-09 | Done
|  | In Ongoing Task List and Closed Task List page, provide ffilter with options - Purchase, Sales, Transfer and All - for Document Type field. (just like schedule order filter pane in Sales Quote list) The data should filter accordingly. |  | R&D for Auto complete Filter possibility to be done by Praduman, else alternate solution to be thought [If not possible, Provide separate pages - need to confirm with Ashok sir]. | 2026-02-23 | Complete by CRM Side | Done |  | 2026-03-06
14 | Business Plan | In "Admin Business Plan", fields sequence should be 2024-25, Actual and then 2025-26. |  |  | 2026-02-23 | Complete | Done |  | 2026-03-03
|  | In BusinessPlan Report page related the filters are not working. |  |  | 2026-02-13 | Complete by CRM Side | Done |  | 2026-03-06
|  | In "Create Business Plan", the Customer Name filter should be showing a dropdown listing all customers. |  |  | 2026-02-23 | Complete by CRM Side | Done |  | 2026-03-06
|  | When used Add product in Business Plan, the product selected and then saved, the same not showing in the plan. | I investigated the issue and found that the data is not updating in the API from Business Central. | Testing to be done by Diya |  | Needs to check testing team |  | Done | 2026-03-09
|  | Blocked products should not appear in the Product selection section in Add product in Business Plan. |  |  |  | Complete by CRM Side | Done |  | 2026-03-06
|  | In Business Plan Approval, require drop down (+) for showing product details under customer instead of clicking the customer and viewing the product details. | Product details to be shown on the customer page itself and should be seen based on "+" icon. We will provide approval functionality in both header (customer) and line (items). If all items approved, header will automatically be approved. If even one item not yet approved then the status will remain send for approval in header also. And, even one line item rejected, then the header will show "Partially Approved" status and when the salesperson will open Business Plan Create page - Partially approved plan of customer, they should be able to make changes in the rejected line items. For that, need to show Item Approval status in the form of words or action in Business Plan details of salesperson. After making changes in the rejected line items details, when saved, the whole plan status should change to "Filled" and the salesperson will be required to send for approval manually. | Check with aditya about the Business Plan Approval - how to know if it is approved or not based on Business plan sp item wise page. PENDING ESTIMATION |  | Hold this issue
Also, they require multiple selection of products for approval and not customers.
|  | They require to view product details - Item category wise in overall every page related to Business Plan. Atleast show a field where the selected product's Item category code appears and require the same in filter. (GACL, GNFC, etc.) |  | Need to make a list of pages where the Item category code to display and discuss the same with Aditya first to check on APIs. |  | Pending by BC Requirement
|  | In Create Business Plan, change caption of Cancel action to Close. Also, when clicked on Close, it should redirect back to the previous page to the same filtered page which was initially selected (Filled, Not Filled, etc.). Currently, on clicking the Cancel action, the user is redirected to the Not Filled filter page as the default filter is set to the same. |  |  | 2026-02-13 | Complete by CRM Side | Done | When clicked on "Close" action after filtering the data as "Filled", the redirected page showed the default filter "Not Filled" instead of "Filled" which was selected. | 2026-03-09
|  | Business Plan report - rework (format provided) |  | Need to show existing CRM report and need to discuss the report format with team |  | Complete by CRM Side |  | Data Mismatch. Also, when clicked on Refresh, Financial Year options were repeated. | 2026-03-06 | Done
Note on D23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No need to remove the daily visit from Dashboard. The purpose is to show the daily visit for that particular day on home page to user. There is no need for filter as requested by Prakash as it has to be of that particular day only
Note on D27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Aditya will create a new page for subform with details of header along with item details. After API is provided pradyuman will provide item filter where we get item list and the value will work like auto complete and the user will be able to filter based on description only.
Note on D28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pradyuman will check possibility for this, require a possibility for action based on the contact directly on the list page. it should perform in a similar way as it is happening currently from card page.
Note on D29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending Estimation from Pradyuman and aditya

## Demo Points
No | Task Description | Issues Remarks | Internal Requirement Gathering Date | Delivery Date | Status | Devevloper Testing Status | Functional Testing Remarks | Testing By Functional Date | Developer Status Remarks after testing / API End point | Assign To
1 | Item Tracking in GRN - Qty. to Receive must not be lesser or greater than defined Lot qty.
2 | In CRM, in Warehouse card page, when clicked on Save, should remain in same page itself and not redirect to List page as now.
3 | Use Transport Qty. field as Qty. to Ship in Warehouse card page and provide as editable with Qty. field validation. Also provide Item Tracking details page just like GRN page with only Qty. to Handle field editable.
4 | Hide or make non-editable - "Approve" and "Reject" actions after Sales Quote Approved. Manage it with Quote Approval Status field on Sales Header only when values are "Approved", "Pending HOD" and "Rejected HOD" for HOD and for Finance - "Approved", "Pending Finance" and "Rejected Finance". Show the status field on card page in CRM.
5 | Provide Warehouse fields non-editable in GRN page in CRM
6 | QC fields validations to be provided in CRM GRN page just as BC.
7 | Issue in partial case in CRM - GRN page - in case of multiple lines, updating Qty. to Receive only in one line and not in other lines.
8 | Freight Charges should be calculated as per Transport Qty. in CRM when selected Transporter Rate card.
9 | In CRM, in existing inquiry, contact name, packing style code not updating
10 | Check product filter in Inquiry in CRM
11 | Customer Name insert - auto fill details in quote header in CRM
12 | Bill to Address and Delivery to Address - default "select" value in Inquiry and Quote both
13 | For approving sales quote, Sales Quote Confirmation action click from mail - after login - Sales Quote should open in case if not logged in.
14 | In Sales Quote Approval mail, GST field - flow GST amount
15 | Screen Design - vertical entry flow - discuss
16 | No data appears in Customer outstanding/Overdue report in Finance login - Sales Quote Status page for Approval.
17 | Purpose of Status field on Inquiry List page as there is no possibility of partial quotations from Inquiry in current developed CRM

## Load API List
API EndPoint Name | Max-Loading Time | API NewEndPoint
EmployeesDotNetAPI | 3.76s
PostCodesDotNetAPI | 1.12s
DimensionValuesDotNetAPI | 943 ms
CountriesRegionsListDotNetAPI | 765 ms
RolesListDotNetAPI | 409 ms
SalespersonPurchaserDotNetAPI | 750 ms
DepartmentsDotNetAPI | 533 ms
CustomerCardDotNetAPI | 2 m 3.18 s | pcplcustomers
AdminBusinessPlan | 1.44 s
ItemDotNetAPI | 7.15 s
BranchListDotNetAPI | 871 ms
pcplcontacts | 4.55 min | pcplcontacts
businessplancustwises | 23.08 s | businessplancustwises
BusinessPlanListDotNetAPI | 894 ms
ContactProductsDotNetAPI | 906 ms
ItemLedgerEntriesDotNetAPI | 5.13 s
SalesQuoteDotNetAPI | 1 m 8.22 s | salesquotes
DailyVisitsDotNetAPI | 1.74 s
StatesListDotNetAPI | 856 ms
AreasListDotNetAPI | 4.25 s
DistrictListDotNetAPI | 1.01 s
IndustryGroupsListDotNetAPI | 497 ms
BusinessTypeListDotNetAPI | 343 ms
SourceofContactsDotNetAPI | 396 ms
SalesOrdersListDotNetAPI | 22.67 s | LatestSalesOrdersListAPI
PostedSalesInvoicesDotNetAPI | 2.41 s
SalesQuotesListDotNetAPI | 5.14 s
InquiryDotNetAPI | 2.13 s
FeedbackHeadersListDotNetAPI | 744 ms
MarketUpdateDotNetAPI | 762 ms
NonPerformingCustomer | 1.58 s
PcplEmployeeList | 505 ms
TargetvsSalesReport | 558 ms
WeeklySalesPlanListDotNetAPI | 756 ms
WeeklyTaskDotNetAPI | 373 ms
MonthlyTask | 357 ms
filteredinquires | 741 ms
filteredsalesorder | 887 ms
filteredsalequote | 839 ms
filteredsaleinoice | 494 ms
itemwisetotalqty | 384 ms
PendingWarehouseSales | 752 ms
PendingWarehousePurchase | 739 ms
FeedbackLinesListDotNetAPI | 816 ms
Feedback | 385 ms
CustomerWiseRatingdetails | 758 ms
CustomerWiseOverAllRatings | 521 ms
GRNSalesOrders | 1.36 s
GRNPurchaseOrders | 818 ms
GRNTransferOrders | 522 ms
PurchaseOrderCardDotNetAPI | 10.19 s | PurchaseOrders
PurchaseLinesDotNetAPI | 2.23 s
SalesReturnOrderDotNetAPI | 845 ms
SalesReturnOrderSubformDotNetAPI | 1.19 s
TransferOrderDotNetAPI | 791 ms
TransferLinesDotNetAPI | 850 ms
APIMngt_GRNPostHeader | 717 ms
ItemTrackingLinesDotNetAPI | 738 ms
APIMngt_InsertUpdateReservationEntryforGRN | 1.29 s
VendorDotNetAPI | 12.68 s | vendors
APIMngt_DeleteReservationEntry | 389 ms
InquiryProductsDotNetAPI | 1.87 s
PaymentTermsDotNetAPI | 1.49 s
ContactBusinessRelationsDotNetAPI | 837 ms
ItemPackingStyleDotNetAPI | 718 ms
CodeunitAPIMgmt_GetShipToAddress | 500 ms
ShiptoAddressDotNetAPI | 851 ms
JobtoAddressDotNetAPI | 731 ms
SalesReceivableSetupDotNetAPI | 701 ms
LocationCardDotNetAPI | 754 ms
MenuListDotNetAPI | 698 ms
NotificationsListDotNetAPI | 525 ms
CustomerLedgerEntriesDotNetAPI | 3.38 s
Daily_Customer_Collection_View_Excel | 2.61 s
LocationByQty | 501 ms
IndustryWiseQty | 807 ms
SalesLinesDotNetAPI | 2.57 s
ReportAPIMngtDotNetAPI_CustomerLedgerReportPrint | 8.19 s
businesstypeindiviual | 1.11 s
industrytypeindiviual | 504 ms
SupportSaleData | 717 ms
weblogreport | 501 ms
CollectionSummaryView | 2.47 s
Transporterdashboard | 828 ms
Inquirymanagement | 2.73 s
salesersonsalequote | 940 ms
Salepersoninquiry | 807 ms
Dailyvisitmonthly | 368 ms
TaskPerformance | 958 ms
Salesperfrmnacebranch | 2.34 s
confirmsalesquote | 848 ms
StockManagement | 900 ms
RoleWiseMenuRightsListDotNetAPI | 927 ms
RolesManagement_GenerateUserPermissionJSON | 502 ms
UserRoleRelation | 492 ms
CompanyInformationDotNetAPI | 605 ms
SalesQuoteSubFormDotNetAPI | 10.31 s | salesquotesubform
OrderedQty | 842 ms
InvoicedQty | 563 ms
SalesOrderCardDotNetAPI | 3.58 s
ShipmentMethodsDotNetAPI | 429 ms
LocationsDotNetAPI | 538 ms
ItemVendorCatalogDotNetAPI | 822 ms
TransportMethodsDotNetAPI | 10.75 s
APIMngt_SalesQuoteReportPrint | 3.03ms
SalesCostSheetLines | 1.12 s
NoSeriesRelDotNetAPI | 927 ms
PurchaseLineCostingDiscountsDotNetAPI | 749 ms
PostedSalesInvoiceLinesDotNetAPI | 1.15 s
ShortCloseReasonDotNetAPI | 398 ms
DispatchDetailsDotNetAPI | 1.26 s
CustomerOverDueDotNetAPI | 839 ms
Transporter_Rate_Details | 757 ms
SiteActivitiesListDotNetAPI | 3.76 s
SiteErrorsListDotNetAPI | 383 ms
VisitTypesDotNetAPI | 398 ms
VisitSubTypesDotNetAPI | 542 ms
postedSalesInvoiceSubformDotNetAPI | 2.24 s
CompetitorsDotNetAPI | 2.25 s
EventMastersDotNetAPI | 541 ms
WeeklySalesPlanCardDotNetAPI | 816 ms
WeeklyPlanSalesPersonWise | 1.86 s
YearlyMonthVisitDotNetAPI | 854 ms
MonthlyVisitsDotNetAPI | 981 ms
DailyVisitProductSubformDotNetAPI | 863 ms
WeeklyVisitTotalTypeWise | 558 ms
WeeklyvisittotalsTypeWiseActual | 643 ms
DailyVisitExpensesDotNetAPI | 877 ms
SalesOrderLineDotNetAPI
Warehouse_Sales_Details | 6.24 s
Warehouse_Purchase_Details | 1.40 s
Warehouse_Transfer_Details | 866 ms
CodeunitAPIMgmt_updateacceptedby | 1.22 s
CodeunitAPIMgmt_updateacceptedbyPurchase | 432 ms
CodeunitAPIMgmt_updateacceptedbyTransfer | 568 ms
APIMngt_CreatePOForProductIncharge | 5.67ms

## Code Unit
Max- API Loading time | CodUnit Link
1.33 s | Uri.EscapeUriString("https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_ModifyAdminBusinessPlan?company=\'Prakash Company\'");
1.45 s | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_UpdateMultipleBusinessPlanCustWiseBySPCode?company=\'Prakash Company\'
1.87 s | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_UpdateSalesPersonCode?company=\'Prakash Company\'
567 ms | https://api.businesscentral.dynamics.com/v2.0/Sandbox/api/pcpl/pcplcrm/v1.0/companies(8e7f221c-b3ab-ee11-a56a-000d3a3e6d80)/feedbackheaderset
902 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CreateAvailableQty_GetAvailableQty?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_DeleteContactProducts?company=\'Prakash Company\'
586 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_GetShipToAddress?company=\'Prakash Company\'
384 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/APIMngt_GetJobToAddress?company=\'Prakash Company\'
406 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_GetNextInqNo?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/DailyCustCollectionMgmt_GenerateCustCollectionReportDate?company=\'Prakash Company\'
30.90 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/InventoryView_GenerateInventoryViewReportDate?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/DeleteDotNetAPIs_deleterolerisemenurights?Company=\'Prakash Company\'
1.38 s | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/DeleteDotNetAPIs_GetNextNo?Company=\'Prakash Company\'
586 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_GetShipToAddress?company=\'Prakash Company\'
458 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/APIMngt_GetJobToAddress?company=\'Prakash Company\'
580 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CreateAvailableQty_GetAvailableQty?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitEventMngt_MakeOrder?company=\'Prakash Company\'
537 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_UpdateInquirytoQuoteandStatus?company=\'Prakash Company\'
573 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/APIMngt_InsertReservationEntry?company=\'Prakash Company\'
553 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/Sales_Cost_Sheet_Mngt_CheckandCreateCostSheet?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/ShortCloseMngt_ShortCloseQuote?company=\'Prakash Company\'
374 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/ShortCloseMngt_ShortCloseQuoteLine?company=\'Prakash Company\'
1.33 s | Uri.EscapeUriString("https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_ModifyAdminBusinessPlan?company=\'Prakash Company\'");
1.45 s | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_UpdateMultipleBusinessPlanCustWiseBySPCode?company=\'Prakash Company\'
1.87 s | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_UpdateSalesPersonCode?company=\'Prakash Company\'
567 ms | https://api.businesscentral.dynamics.com/v2.0/Sandbox/api/pcpl/pcplcrm/v1.0/companies(8e7f221c-b3ab-ee11-a56a-000d3a3e6d80)/feedbackheaderset
902 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CreateAvailableQty_GetAvailableQty?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_DeleteContactProducts?company=\'Prakash Company\'
586 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_GetShipToAddress?company=\'Prakash Company\'
384 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/APIMngt_GetJobToAddress?company=\'Prakash Company\'
406 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_GetNextInqNo?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/DailyCustCollectionMgmt_GenerateCustCollectionReportDate?company=\'Prakash Company\'
30.90 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/InventoryView_GenerateInventoryViewReportDate?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/DeleteDotNetAPIs_deleterolerisemenurights?Company=\'Prakash Company\'
1.38 s | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/DeleteDotNetAPIs_GetNextNo?Company=\'Prakash Company\'
586 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_GetShipToAddress?company=\'Prakash Company\'
458 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/APIMngt_GetJobToAddress?company=\'Prakash Company\'
580 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CreateAvailableQty_GetAvailableQty?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitEventMngt_MakeOrder?company=\'Prakash Company\'
537 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/CodeunitAPIMgmt_UpdateInquirytoQuoteandStatus?company=\'Prakash Company\'
573 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/APIMngt_InsertReservationEntry?company=\'Prakash Company\'
553 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/Sales_Cost_Sheet_Mngt_CheckandCreateCostSheet?company=\'Prakash Company\'
https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/ShortCloseMngt_ShortCloseQuote?company=\'Prakash Company\'
374 ms | https://api.businesscentral.dynamics.com/v2.0/e55ad508-ef1a-489f-afe3-ae21f856e440/Sandbox/ODataV4/ShortCloseMngt_ShortCloseQuoteLine?company=\'Prakash Company\'